# Description of the Action

Title of the action: "Demo Rights Programme for Testing"

The implementation period of the action shall be 24 months and shall start on 1 March 2026.

# Action plan

| Activity | Lead | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1: Laws reviewed |  |  |  |  |  |  |  |
| 1.1 Needs assessment | CoE | P | P | X | X |  |  |
| 1.2 Expert review | CoE |  |  | X | X | X |  |
| Output 2: Capacity built |  |  |  |  |  |  |  |
| 2.1 Training of trainers | CoE |  |  |  | X | X | X |

# Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Staff turnover | High | Medium | Backup staffing |
| Political change | Low | Very high | Dialogue |

# Logical framework

| Result | Indicator | Baseline | Target |
| --- | --- | --- | --- |
| Outcome 1 | Number of laws aligned | 0 | 3 |
|  | Judges trained | 0 | 200 |